## Sheet1
Meeting Date and Time:
Name | What I did last week | What will I do next | Any impediments?
Julian Pryde | Create class skeletons, write Robot.move() algorithm | Write Robot.move() code, write basic IO.log() and IO.sendToGUI() code for product preview | No
Savanh Lu | Write GUI algorithm, start GUI code | Finish writing GUI code | No
Miralda Rodney | Write sensor.sense() algorithm | Write sensor.sense() code | No
Stephen Kristin | Start writing algorithm to generate ref. Points | Finish algorithm for ref. Points, Write code creating ref. Points | No
Meeting Date and Time: | 4March2016 3:00pm
Name | What I did last week | What will I do next | Any impediments?
Julian Pryde | Write code for Main class and Robot.move() | Help to interface Robot.move() and Main.main() with other methods | no
Savanh Lu | Finished user input code | fix start simulation button | no
Miralda Rodney | Write code to sense points, save and read from file | Add sensor error, pass information to robot | exception handling in file i/o
Stephen Kristin | Write code for map class, interface with sensor class | Prepare for sprint 2 | no
Meeting Date and Time: | 11March2016
Name | What I did last week | What will I do next | Any impediments?
Julian Pryde | Interface Robot.move with Sensor.sense(), prepare for presentation | Plan for sprint 2 | Error in Robot class
Miralda Rodney | Pass information on sensed points to robot | Plan for sprint 2 | no
Savanh Lu | fixed simulation button | Plan for sprint 2 | no
Stephen Kristin | Prepare for Presentation | Plan for sprint 2 | Error in Robot class
Meeting Date and Time: | 14March16
Name | What I did last week | What will I do next | Any impediments?
Miralda Rodney | read file with saved ref points, added sensing with error, added finding the distance between robot and different reference points, added finding the angle when robot is at one point and two ref points are in its scope | Calculate Robot X and Y position from found ref points | how to track >2 points at one time
Savanh Lu | - | Label GUI, start graphing | no
Julian Pryde | - | Write data from run to a file | no
Stephen Kristin | - | Parse data from file | Could not be at meeting
Timea and date: | 25March16
Name | What I did last week | What will I do next | Any impediments?
Miralda Rodney | Tested sensor.detectPoints(), fixed error in detectPoints, fixed javadocs for detectPoints, started writing code to determine robot's location (finding reference points), created I/O method in sensor class | Create switch statements for different numbers of detected points | Switch statement not working
Savanh Lu | Graphs of final output | Finish graphs, create array of data from each run | Graphs not working
Julian Pryde | Testing Robot.move | Finish tests for Robot.move(), Begin writing code to make robot move | no
Stephen Kristin | Test map class, make map class work | Start file scan function | Issues with pulling from GitHub
Time and date: | Tuesday- 4/5/2016
Name | What I did last week | What will I do next? | Impediments?
Miralda
Savanh | create dummy data for chart | use dummy data for start button | GitHub- can't commit/push
Julian | had military obligations | work on I/O
Stephen | added info page to GUI | work on I/O | scheduling with julian to work on IO
Time and date: | Friday- 4/8/2016
Name: | What I did last week | What will I do next? | Impediments?
Savanh | research ball bouncing on screen, work on test plan. | fix launch error for chart and use dummy data to start the start button | N/A
Julian | built file output from a run, fixed some bugs within robot class | fix more bugs in robot and in map class | N/A
Miralda | troubleshoot github, figured out robot location, added try throw catch | test cases, test plan, and troubleshooting, output robotsd location to a file | N/A
Stephen | I/O things | work on test cases and test plan | N/A
Time and date: | Friday- 4/15/2016
Name: | What I did last week | What will I do next? | Impediments?
Savanh | Found animation code and fix double launch error | add user parameters, work on the bouncing ball animation, and write test cases | N/A
Julian | fixed robot.move() function | integrating everything so it works | N/A
Miralda | debugged program and written a few test cases | optimize her class, more testing and fixing her own code. | N/A
Stephen | test plan document and test the map class | help trouble shoot, testing, and helping Sav with the bouncing ball animation. | N/A
Time and date: | Friday-4/22/16
Name: | What I did last week | What will I do next? | Impediments?
Savanh | Add user parameters | junit testing, final documentation, and add actual data to chart. | N/A
Julian | fixed robot.move() to not allow negative values | Create junit tests and finish final documentation | N/A
Miralda | Wrote test cases and comments for javadoc and created a JAR file | finish testing and final documentation | N/A
Stephen | Met with Savanh to figure out the bouncing ball function | work on Junit testing and final documentation | N/A
Time and date: | Tuesday 4/26/16
name: | What I did last week | What will I do next? | Impediments?
Savanh | Documentaion | Documentation | N/A
Julian | Made file I/O work properly, started workig on user manual, and fixed some bugs in his class | Final documentation &polish the program | N/A
Miralda | Changed entire sensor class and worked on documentation | Documentation | N/a
Stephen | Documentaion | documentation | N/A