## Sheet1
Features | Estimate: Hours | Priority | Acceptance criteria
display to start robot simulation | 1 Hour | 1 | gui runs
user input | 2 Hours | 2 | accepts user input and handles errors, simulation runs
generate ref points | 8 Hours | 3 | rng works with unique seeds
simulate map | 1 Hour | 4 | map exists for reference points to exist
simulate robot movement w/ error | 5 Hours | 5 | robot class returns/updates its location everytime it "moves" to sensor class
simulate sensor(s) | 10 Hours | 6 | sensors detect points
robot determines location | 10 Hours | 7 | robot performs math from known reference points to determine location
record sensed location | 2 Hours | 8 | sensor class records location of point and calls the calculations class
robot records location of ref points | 4 Hours | 9 | sends to the IO class to be saved in file
robot saves raw data in a log file | 20 Hours | 10 | simulation data sent to log file
robot recalls data from log file | 20 Hours | 11 | simulation data loaded from log file
Display graphs of run stats | 7 Hours | 12 | series of iterations stored in memory are converted into graphs for user to view