## Sprint 1
To Do: | Assigned To: | In Progress: | Done? | Deadline: | Sprint | Total Hours | Hours to Complete | Unplanned Items | Day (starts on 15Feb) | Estimated Hours to complete | Actual Hours left to complete
Items in 1st Sprint | [8 empty] | 1 | 34 | 35
user input | Savanh | yes | yes |  | 1 | 2 | 2 |  | 2 | 32 | 35
generate ref points | Stephen | yes | yes |  | 1 | 8 | 8 |  | 3 | 30 | 35
simulate robot movement w/ error | Julian | yes | yes |  | 1 | 5 | 5 |  | 4 | 29 | 35
simulate sensors | Miralda | yes | yes |  | 1 | 20 | 20 |  | 5 | 27 | 35
display to start robot simulation | Savanh | yes | yes |  | 1 | 1 | 1 |  | 6 | 25 | 35
[6 empty] | Total: 36 | Total: 36 |  | 7 | 24 | 35
[6 empty] | 36 |  |  | 8 | 22 | 35
[9 empty] | 9 | 20 | 35
[9 empty] | 10 | 18 | 35
[9 empty] | 11 | 17 | 30
[9 empty] | 12 | 15 | 29
[9 empty] | 13 | 13 | 29
[9 empty] | 14 | 12 | 29
[9 empty] | 15 | 10 | 29
[9 empty] | 16 | 8 | 9
[9 empty] | 17 | 6 | 2
[9 empty] | 18 | 5 | 2
[9 empty] | 19 | 3 | 1
[9 empty] | 20 | 1 | 1
[9 empty] | 21 | 0 | 0

## Sprint 2
To Do: | Assigned To: | In Progress: | Done? | Deadline: | Total Hours | Hours to Complete | Unplanned Items | Day | Estimated Hours to complete
Items in 2nd Sprint (Subject to change) | [7 empty] | 1 | 55
robot determines location |  | yes |  |  | 10 | 10 |  | 2 | 53
Finding range to sensed ref points | Miralda |  | yes
Find bearing to sensed ref points | Miralda |  | yes
find position from sensed points for every move | Miralda |  | yes
robot saves raw data in a log file |  |  |  |  | 20 | 20 |  | 5 | 47
Create file for run | Julian |  | yes
Write run data to file | Julian |  | yes
save actual versus error in location | Julian |  | yes
save sensed points | Julian |  | yes
sensor
sense a reference point | Miralda |  | yes
add error to sensed reference point | Miralda |  | yes
track one reference point as robot moves (distance) | Miralda |  | yes
track multiple reference points (recognize multiple points) | Miralda |  | yes
determine angle between robot and several reference points | Miralda |  | yes
calculate robot's position (x, y) relative to two reference points (maybe more) | Miralda |  | yes
robot recalls data from log file |  |  |  |  | 20 | 20 |  | 6 | 45
Parse data from log file | Stephen |  | yes
load parsed data to new run | Stephen |  | yes
display graph of sensor and movement error from log file |  |  |  |  | 7 | 7 |  | 7 | 43
Create array of all calculated positions | Savanh
Create array of all actual positions | Savanh |  | yes
Create array of difference between actual and calculated positions | Savanh |  | yes | [6 empty] | Actual hours to complete
Create graph of each array vs. move number | Savanh |  | yes
GUI |  |  |  |  | Total: 57 | Total: 57
Add functionality to menu options | Stephen |  | yes |  | 57
Finalize visual apperance | Stephen |  | yes
Add output pane for graphs | Savanh |  | yes
-Break down items
-Create new github repo
[5 empty] | -fix bug |  |  | 1 | 55 | 57
[5 empty] | -start code on new sprint |  |  | 2 | 53 | 57
[8 empty] | 3 | 51 | 55
[8 empty] | 4 | 49 | 53
[8 empty] | 5 | 47 | 53
[8 empty] | 6 | 45 | 53
[8 empty] | 7 | 43 | 52
[8 empty] | 8 | 41 | 50
[8 empty] | 9 | 39 | 50
[8 empty] | 10 | 38 | 50
[8 empty] | 11 | 36 | 50
[8 empty] | 12 | 34 | 50
[8 empty] | 13 | 32 | 50
[8 empty] | 14 | 30 | 50
[8 empty] | 15 | 28 | 50
[8 empty] | 16 | 26 | 45
[8 empty] | 17 | 24 | 42
|  |  | Things to Output |  |  |  |  | 18 | 22 | 40
|  |  | Movement error |  |  |  |  | 19 | 20 | 38
|  |  | Sensor error |  |  |  |  | 20 | 19 | 30
|  |  | Calculated positions of robot |  |  |  |  | 21 | 17 | 25
|  |  | Actual positions of robot |  |  |  |  | 22 | 15 | 25
[8 empty] | 23 | 13 | 25
[8 empty] | 24 | 11 | 25
[8 empty] | 25 | 9 | 20
[8 empty] | 26 | 7 | 13
[8 empty] | 27 | 5 | 5
[8 empty] | 28 | 3 | 3
[8 empty] | 29 | 1 | 1
[8 empty] | 30 | 0 | 0